## WBS
PROJECT WORK BREAKDOWN STRUCTURE
# | UC No. | Function/Screen | Feature | Level* | Priority | Function/Screen Details | Planned | Status |  |  |  |  | Estimate
[8 empty] | SRS | SDD | Backend | Mobile | Test | SRS | SDD | Backend | Mobile | Test
1 | 1.1 | Register Account | Authenticate & Authorize | Medium | High | Register to become a student | Iteration 1 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 1 | 1.5 | 0.5
2 | 1.2 | Login/Logout Account | Authenticate & Authorize | Medium | High | Log in to account with email/phone + password, or via Google or Facebook | Iteration 1 | Done | Done | Done | Done | Done | 1 | 1.5 | 2.5 | 2.5 | 1
3 | 1.3 | Reset Password | Authenticate & Authorize | Simple | High | Reset password in login window | Iteration 1 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
4 | 1.4 | Change Password | Authenticate & Authorize | Simple | High | Change current password to new password in account profile | Iteration 1 | Done | Done | Done | Done | Done | 0.6 | 0.8 | 0.5 | 0.5 | 0.5
5 | 2.1 | Search User | Search User & Manage Profile | Medium | High | Admin/student/moderator find mentor/student/moderator by filter condition | Iteration 2 | Done | Done | Done | Done | Done | 0.6 | 0.6 | 1 | 1 | 0.6
6 | 2.2.1 | View Profile | Search User & Manage Profile | Simple | High | View the account profile of the role itself (student, mentor, moderator, admin) | Iteration 1 | Done | Done | Done | Done | Done | 1.5 | 2.8 | 2.5 | 1.5 | 1.2
7 | 2.2.2 | Update Profile | Search User & Manage Profile | Medium | High | Edit the account profile of the role itself (student, mentor, moderator, admin) | Iteration 1 | Done | Done | Done | Done | Done | 2 | 2 | 2 | 1.5 | 1.2
8 | 2.2.3 | Upload Avatar | Search User & Manage Profile | Medium | Medium | Upload avatar to change current avatar | Iteration 1 | Done | Done | Done | Done | Done | 0.5 | 0.6 | 0.6 | 0.5 | 0.5
9 | 3.1.1 | View Student List | Manage Student | Simple | High | Admin/Moderator view student list | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 1.5 | 0.5
10 | 3.1.2 | View Student Profile | Manage Student | Simple | High | Admin/Moderator view student profile | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
11 | 3.1.3 | Active/Inactive Student | Manage Student | Simple | High | Admin/Moderator active/inactive student | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
12 | 4.1.1 | View Mentor List | Manage Mentor | Simple | High | Admin/Moderator view mentor list | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 1 | 0.5
13 | 4.1.2 | Active/Inactive Mentor | Manage Mentor | Simple | High | Admin/Moderator active/inactive mentor account | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
14 | 4.1.3 | View Registered Mentor List | Manage Mentor | Simple | High | Admin/Moderator view registered mentor list | Iteration 2 | Done | Done | Done | Done | Done | 0.6 | 0.6 | 0.5 | 1 | 0.5
15 | 4.1.4 | View Mentor Registration Profile | Manage Mentor | Simple | High | Admin/Moderator view registered mentor registration profile | Iteration 2 | Done | Done | Done | Done | Done | 0.8 | 0.9 | 0.5 | 0.5 | 0.5
16 | 4.1.5 | Approve/Reject Mentor | Manage Mentor | Simple | High | Admin/Moderator approve/reject registered mentor registration profile | Iteration 2 | Done | Done | Done | Done | Done | 0.8 | 0.7 | 0.5 | 0.2 | 0.5
17 | 4.2 | View Top Mentor List | Manage Mentor | Simple | High | Student view top mentor list | Iteration 2 | Done | Done | Done | Done | Done | 0.8 | 0.8 | 0.5 | 1 | 0.5
18 | 4.3.1 | View Favorite Mentor List | Manage Mentor | Simple | Medium | Student view favorite mentor list | Iteration 3 | Done | Done | Done | Done | Done | 0.9 | 0.6 | 0.5 | 1 | 0.5
19 | 4.3.2 | Add Favorite Mentor | Manage Mentor | Simple | Medium | Student add mentor to favourite mentor list | Iteration 3 | Done | Done | Done | Done | Done | 0.8 | 0.8 | 0.5 | 0.2 | 0.5
20 | 4.3.3 | Delete Favorite Mentor | Manage Mentor | Simple | Medium | Student remove mentor from favorite mentor list | Iteration 3 | Done | Done | Done | Done | Done | 0.8 | 0.8 | 0.5 | 0.2 | 0.5
21 | 4.4 | View Mentor Profile | Manage Mentor | Simple | High | Student, moderator and admin view mentor profile | Iteration 2 | Done | Done | Done | Done | Done | 0.8 | 0.8 | 0.5 | 0.5 | 0.5
22 | 5.1.1 | View Moderator List | Manage Moderator | Simple | High | Admin view moderator list | Iteration 2 | Done | Done | Done | Done | Done | 0.8 | 0.8 | 0.5 | 1 | 0.5
23 | 5.1.2 | View Moderator Profile | Manage Moderator | Medium | High | Admin view moderator profile | Iteration 2 | Done | Done | Done | Done | Done | 0.8 | 0.8 | 0.5 | 0.5 | 0.5
24 | 5.1.3 | Add Moderator | Manage Moderator | Medium | High | Admin add new moderator(s) | Iteration 2 | Done | Done | Done | Done | Done | 0.8 | 0.8 | 1 | 0.5 | 0.5
25 | 5.1.4 | Active/Inactive Moderator | Manage Moderator | Simple | High | Admin active/deactive moderator(s) | Iteration 2 | Done | Done | Done | Done | Done | 0.8 | 0.8 | 0.5 | 0.5 | 0.5
26 | 6.1.1 | View Favorite Quiz List | Manage Quiz | Simple | Medium | View favourite quiz list | Iteration 3 | Done | Done | Done | Done | Done | 0.8 | 0.6 | 0.5 | 0.5 | 0.5
27 | 6.1.2 | Add Favorite Quiz | Manage Quiz | Medium | High | Add quiz to the favourite list | Iteration 3 | Done | Done | Done | Done | Done | 0.8 | 0.8 | 1 | 0.5 | 0.5
28 | 6.1.3 | Delete Favorite Quiz | Manage Quiz | Simple | Medium | Remove quiz from favourite list | Iteration 3 | Done | Done | Done | Done | Done | 0.8 | 0.8 | 0.5 | 0.2 | 0.5
29 | 6.2 | Take Quiz | Manage Quiz | Complex | High | Student/Guest do the quiz | Iteration 2 | Done | Done | Done | Done | Done | 1.3 | 1.2 | 2 | 2.5 | 0.5
30 | 6.3 | View Taken Quiz History | Manage Quiz | Medium | High | View list of taken quiz in the past | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 1 | 1.5 | 0.5
31 | 6.4 | View Quiz Detail Result | Manage Quiz | Simple | High | View quiz result: score, which answer true/false | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 1 | 0.5
32 | 6.5 | View Quiz List | Manage Quiz | Simple | High | View quiz list (include filter) | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 1 | 0.5
33 | 6.6 | View Quiz Overview | Manage Quiz | Simple | High | View quiz title, number of questions, time | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
34 | 6.7.1 | View Quiz Detail | Manage Quiz | Medium | High | View quiz detail (all questions & answers) | Iteration 2 | Done | Done | Done | Done | Done | 1 | 0.8 | 1 | 1.5 | 0.5
35 | 6.7.2 | Create Quiz | Manage Quiz | Complex | High | Create new quiz by add questions one by one, upload draft quiz | Iteration 2 | Done | Done | Done | Done | Done | 1 | 1 | 2 | 1.5 | 1
36 | 6.7.3 | Update Quiz | Manage Quiz | Medium | High | Mentor/Moderator edit the quiz: question, answer, quiz overview (title, time) | Iteration 2 | Done | Done | Done | Done | Done | 1.2 | 1 | 1 | 1 | 0.6
37 | 6.7.4 | Delete Quiz | Manage Quiz | Simple | High | Delete quiz | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
38 | 6.7.5 | View Draft Quiz List | Manage Quiz | Simple | Medium | View list of draft quiz that user created | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 1 | 0.5
39 | 6.7.6 | View Own Quiz List | Manage Quiz | Simple | Medium | View list of published quiz that user created | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 1 | 0.5
40 | 6.7.7 | Publish Draft Quiz | Manage Quiz | Medium | Medium | Publish a draft quiz | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 1 | 0.5 | 0.5
41 | 6.7.8 | Search Quiz | Manage Quiz | Medium | Medium | Search a quiz | Iteration 3 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.6 | 0.6 | 0.6
42 | 7.1 | Create Mentor-finding Post | Manage Mentor-finding Post | Medium | High | Student create a mentor-finding post | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 1 | 1.5 | 0.6
43 | 7.2 | View On-going Mentor-finding Post List | Manage Mentor-finding Post | Simple | High | Student view on-going mentor-finding post list | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 1 | 0.5
44 | 7.3 | View Completed Mentor-finding Post List | Manage Mentor-finding Post | Simple | High | Student view completed mentor-finding post list | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 1 | 0.5
45 | 7.4 | View Cancelled Mentor-finding Post List | Manage Mentor-finding Post | Simple | High | Student view cancelled mentor-finding post list | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 1 | 0.5
46 | 7.5 | Cancel Mentor-finding Post | Manage Mentor-finding Post | Simple | High | Student cancel mentor-finding post | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
47 | 7.6 | Mark Completed Mentor-finding Post | Manage Mentor-finding Post | Simple | High | Student mark mentor-finding post completed | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
48 | 7.7 | View Student’s Mentor-finding Post List | Manage Mentor-finding Post | Medium | High | Mentor view all student's mentor-finding post list, order by descending time | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 1 | 1 | 0.6
49 | 7.8 | View Mentor-finding Post Detail | Manage Mentor-finding Post | Simple | High | User view detail mentor-finding post | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 1 | 0.5
50 | 7.9 | Search Mentor-finding Post | Manage Mentor-finding Post | Medium | High | Mentor search mentor-finding post | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 1 | 1 | 0.6
51 | 7.1 | Like/Unlike Post | Manage Mentor-finding Post | Medium | High | User like or unlike a post | Iteration 3 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.6 | 2 | 0.5
52 | 7.11 | Add Comment | Manage Mentor-finding Post | Medium | High | User add a comment to the post | Iteration 3 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.6 | 2 | 0.5
53 | 7.12 | Delete Comment | Manage Mentor-finding Post | Medium | High | User delete an existed comment that created by himself/herself | Iteration 3 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.6 | 2 | 0.5
54 | 7.13 | View Liked User List | Manage Mentor-finding Post | Medium | High | User view all users that liked the post | Iteration 3 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.6 | 2 | 0.5
55 | 7.14 | View Comment List | Manage Mentor-finding Post | Medium | High | User view all comments of the post | Iteration 3 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.6 | 2 | 0.5
56 | 8.1 | View Pending Mentorship Request | Manage Mentorship Request | Simple | High | Student/Mentor views all mentorship request corresponding to his/her | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.6 | 1 | 0.5
57 | 8.2 | View Accepted Mentorship Request List | Manage Mentorship Request | Simple | High | Student/Mentor views all accepted mentorship request corresponding to his/her | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.6 | 1 | 0.5
58 | 8.3 | View Rejected Mentorship Request | Manage Mentorship Request | Simple | High | Student/Mentor views all rejected mentorship request corresponding to his/her | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.6 | 0.5 | 0.5
59 | 8.4 | View Detail Mentorship Request | Manage Mentorship Request | Medium | High | Student/Mentor views detail mentorship request corresponding to his/her | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.6 | 2 | 0.5
60 | 8.5 | Accept Mentorship Request | Manage Mentorship Request | Medium | High | Mentor approve mentorship request | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 1 | 0.5 | 0.6
61 | 8.6 | Reject Mentorship Request | Manage Mentorship Request | Medium | High | Mentor reject mentorship request | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 1 | 0.5 | 0.6
62 | 8.7 | Cancel Mentorship Request | Manage Mentorship Request | Medium | High | Student cancel mentorship request | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
63 | 8.8 | Book Mentorship Request | Manage Mentorship Request | Medium | High | Student book mentorship request | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 1 | 1.5 | 0.6
64 | 9.1 | Feedback Mentor | Feedback | Medium | Medium | Student feedback mentor | Iteration 3 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 1 | 0.5 | 0.6
65 | 9.2 | View Feedback | Feedback | Simple | Medium | Student/Mentor view feedback | Iteration 3 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 0.5 | 0.6
66 | 10.1.1 | View Conversation List | Contact | Simple | High | View conversation list between mentor & student | Iteration 3 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 1 | 0.6
67 | 10.1.2 | Chat | Contact | Complex | High | Direct chat together or leave messages | Iteration 3 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 2 | 2 | 0.6
68 | 11.1 | View Schedule | Manage Schedule | Complex | High | View detail schedule (Mentor/Student) | Iteration 2 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 2 | 2 | 0.6
69 | 11.2 | View Event Detail | Manage Schedule | Medium | High | View detail event (Mentor/Student) | Iteration 3 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.6 | 0.3 | 0.6
70 | 12.1 | View Notifcation List | Notification | Simple | High | View list of notification | Iteration 3 | Done | Done | Done | Done | Done | 0.5 | 0.5 | 0.5 | 0.5 | 0.6
[13 empty] | 45.1 | 46.2 | 55.2 | 68.7 | 39 | 254.2
(*) You can rate the functions' complexity based on the number of fields on the screens/the number
of transactions in the function, with the details as below:
| simple | <=3 transactions
| medium | <= 7 transactions
| complex | > 7 transactions
In which: fields: screen components or database table fields
transactions: action buttons, user or database transactions

## Issues
PROJECT ISSUES
# | Issue | Potential Impact | Priority | Owner | Open Date | Close Date | Status | Notes
1 | Mentor đã submit đủ thông tin rồi và đang đợi verify thì có được update profile ko? |  | Medium | ThuyNDT | 2022-03-02 | 2022-03-07 | Closed | ko đc update profile
2 | Mentor bị reject thì tiếp theo business flow như nào? |  | Medium | ThuyNDT | 2022-03-02 | 2022-03-07 | Closed | chuyển thành role student. *Note: sau
3 | Màn hình home của mentor chờ verify. Nãy bàn là để function của nó cơ bản giống guest, nhưng nó dki mentor mà show list mentor nó lại k hợp lí. Mình nên hiển thị những thông tin nào nhỉ? |  | Medium | ThuyNDT | 2022-03-02 | 2022-03-07 | Closed | màn Home vẫn hiển thị như Guest, nhưng ko book đc mentor khác.
4 | Màn hình chọn address: nên đổi thành chọn tỉnh/thành phố, quận/huyện, xã/phường |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
5 | gender trong database của user_profile thấy có, nhưng trên màn hình profile thì ko có |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | SRS chưa thấy chỗ nào cần đề cập đến view gender, nhưng đã update choose gender ở các màn thêm info r. Design có gender dưới dạng symbol gần tên
6 | Năm sinh ở màn Add more info đang thấy ko điền đc dạng ngày tháng năm? |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | database đổi thành chỉ lưu năm sinh, ko lưu ngày sinh
7 | Trường học và năm sinh có bắt buộc cần phải điền khi account đăng ký dạng mentor hay ko? |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
8 | Đăng nhập bằng facebook/gmail đang pending => chưa test đc |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | tạm thời bỏ.
9 | khi quá thời gian OTP rồi thì button Xác nhận nên deactive luôn. khi chưa nhập hết token thì cũng deactive button luôn. |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | cần update SRS
10 | khi quá thời gian OTP sẽ ko tính là 1 lần nhập sai. |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | pending, check lại sau
11 | Tài khoản đã bị khóa thì làm như thế nào để mở lại? |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Sau 1 tiếng, đã có trong Business Rule
12 | database bảng user_profiles chưa lưu thông tin <Chuyên môn> khi nhập ở màn Add more info |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Dựa vào profiles_categories
13 | Sửa UC-1: - Bổ sung Exception: Khi nhập mật khẩu sai format => Hiển thị MSG-15 - Bổ sung Normal Flow: khi click OK trên dialog thì di chuyển về màn Home - Bổ sung Alternative Flow: khi click icon <Cancel> => di chuyển về màn Login - Bổ sung thêm 2 UC con: (2022/03/05 chưa bổ sung bên test) + UC 1.1: Add more info with student role + UC 1.2: Add more info with mentor role + UC 1.3: Choose address (Bổ sung thêm màn hình chọn address ở phần function) + UC 1.4: Choose subject (Bổ sung thêm màn hình chọn chuyên môn ở phần function) |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
14 | Chỉnh lại màn hình <Common Register>: - Tthêm trường: Bạn muốn đăng ký là... - xóa <Đồng ý với...> - trường số điện thoại ko bắt buộc => bỏ dấu * đi - đổi Nhập lại mật khẩu => Xác nhận mật khẩu |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
15 | Sửa UC-2: - Bổ sung Pre-condition: Có thể kết nối đến server (bổ sung này cần triển khai ngang trên toàn bộ các usecase) - Primary Actor: bổ sung admin và moderator - Diagram: vẽ thêm secondary actors. - Bổ sung thêm Alternative Flow: khi người dùng click button <Bỏ qua đăng nhập> => Di chuyển tới màn Home với role Guest - Bổ sung Post Conditions: + If it already has an account with the same email as the Google/Facebook account, sync will be done. + In other cases, the Google/Facebook account will be created by student role. |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
16 | Màn hình Logic sửa: <Email> => <Email/Số điện thoại> |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
17 | Udpate lại tất cả các màn hình trong SRS cho khớp với màn đã design (ít nhất là các màn nằm ở IT1 trước ngày 7/3) |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
18 | Sửa lại các tên button thành tiếng việt |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
19 | Content của các message hiện đã được update liên tục khi thực hiện viết testcase, chú ý lấy file SRS baseline từ link note ở phía trên (folder Working Process) để đồng bộ với nhau, ko bị conflict. |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
20 | Sửa UC-3: - Thêm Alternative Flow: khi click button <Quay trở lại Đăng nhập> hoặc icon <Cancel> ở màn Forgot Password => quay về màn Login; khi click icon <Cancel> ở màn Reset Password => quay về màn <Forgot Password> |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
21 | Sửa UC 3.1: - Thêm alternative flow: khi click button <Gửi lại>; khi click icon <Cancel>; khi nhập sai quá 6 lần liên tiếp |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
22 | Ở mỗi UC đều thấy ghi Pre-condition là Có kết nối internet + server, nhưng khi đến Exception thì lại có lỗi khi ko kết nối đến interrnet/server. => ko hợp lý + tốn effort tạo testcase. => Cần thực hiện bỏ đi điều kiện Precondition + Exception đối với việc kết nối interrnet/server và bỏ vào Buseniss Rule. |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
23 | Sửa UC 4: - Bổ sung alternative flow: khi clikc icon <cancel> |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
24 | Bổ sung thêm các màn hình sau ở phần 3- Function: 1. Màn chọn address 2. Màn chọn subject 3. Màn Setting 4. xóa màn hình <Choose role to regist> 5. Preview Avatar: Màn hình preview avatar trước khi confirm thay đổi avatar 6. Màn Student Profile - khi admin chọn 1 student trong list và show lên profile của student đó để active/deactive (đang chưa thấy có mô tả cho màn này nhưng vẫn có mô tả UC, hình như bị nhầm giữa Student Profile từ hướng nhìn của user và Student Profile từ hướng nhìn của admin) 7. Màn Mentor Profile - khi admin chọn 1 mentor trong list và show lên profile của mentor đó |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
25 | Cần họp đánh giá: Khi từ role Student thực hiện đăng ký trở thành Mentor thì các mentorship request trước đó của nó có bị xóa đi ko? Nếu bị ảnh hưởng nhiều thì thực hiện bỏ đi function này, nếu ko thì cần đánh giá xem sửa SRS và code ntnt. |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
26 | Sửa UC-5: - Update lại các thông tin cần nhập vào là : Chuyện môn + dạy online hay offline - Thêm alternative flow: khi click icon <Cancel> => về lại màn Profile. |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
27 | Sửa UC-6: - Thêm alternative flow: khi click icon <Cancel> => về lại màn Profile. (ở cả 3 UC con) - UC 6.2: sửa lại luồng đi vào là click icon <Edit> chứ ko phải click icon <Profile> |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
28 | Giả sử có người muốn lập 2 nick, 1 nick student để học và 1 nick mentor để dạy, khi đó người dùng muốn dùng cùng 1 số điện thoại để liên lạc thì hệ thống sẽ ko cho phép. Như vậy có hợp lý hay ko? |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Xem xét, nếu có thời gian sẽ sửa lại cho hợp lý.
29 | Sửa UC-7.3: - Đang mô tả sai Post-Condition, sửa như sau: + Nếu student accoutn đang active => chuyển sang deactive + Nếu student account đang deactive => chuyển sang active - Update thêm Alternative Flow: khi ở màn Student List và click dấu 3 chấm ở tab student bất kì => dropdown lựa chọn active/deactive |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
30 | Bổ sung thêm UC 2.1: Logout account |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
31 | Sửa UC-7.1, 8.1, 8.3 & 8.5: - Exception khi ko có mentor nào trong list: bỏ đi mess cảnh báo; Hiển thị các text tương ứng sau: <Hiện chưa có gia sư nào> <Hiện chưa có học sinh nào> <Hiện chưa có gia sư nào bị tố cáo> <Hiện chưa có đơn đăng ký gia sư nào>) - Thêm business order theo thứ tự created time |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
32 | Sửa lại các màn hiển thị list người dùng của role admin: nên update thêm trường active/deactive status của người dùng để nhìn vào sẽ biết luôn acc nào bị khóa/acc nào đang ko bị khóa. |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
33 | Sửa 7.3 & 8.4: - Bổ sung Alternative Flow: khi đi từ màn Student Profile/Mentor Profile thì click button <Khóa>/<Kích hoạt> để thực hiện active/deactive account. - Bổ sung thêm dialog confirm trong Normail Flow: <Bạn có chắc chắn muốn khóa tài khoản người dùng này?> <Bạn có chắc chắn muốn kích hoạt tài khoản người dùng này?> |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
34 | Sửa 8.7: - Bổ sung Alternative Flow: khi đi từ màn Mentor Profile thì click button <Duyệt/Từ chối> để thực hiện approve/reject account. - Bổ sung thêm dialog confirm trong Normail Flow: <Cho phép người dùng trở thành gia sư?> <Hủy yêu cầu trở thành gia sư?> |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
35 | Sửa UC 9.0: - Exception khi ko có mentor nào trong list: bỏ đi mess cảnh báo; Hiển thị các text tương ứng sau: <Hiện chưa có gia sư nào> - Thêm business order theo thứ tự created time |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
36 | Sửa UC 12: - Bổ sung alternative flow: + Khi chọn trên Mentor List (role admin/moderator) + Khi chọn trên Registered Mentor List (role admin/moderator) + Khi chọn trên Top Mentor List (role student/guest) + Khi chọn trên Filtered Mentor List (role admin/moderator) + Khi chọn trên Filtered Mentor List (role student/guest) |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
37 | UC Login Account thiếu Alternative Flow:khi ở màn Home của Guest, click option <Đăng nhập ngay để kết nối với gia sư> |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
38 | Lúc thì là gia sư, lúc thì là giảng viên => cần design thống nhất lại là gia sư |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
39 | UC-7.0: Thêm alternative flow: Khi click 1 student từ 1 list student đã qua filtered. |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
40 | UC Login chưa có mô tả trường hợp đăng nhập vào 1 tài khoản đang bị khóa. |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
41 | Những UC của feature Quiz Management + Mentorship Management hiện chưa đúng với design. |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
42 | Khi student click vào tab <Yêu cầu> trên navbar thì hiển thị màn gì? |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
43 | Gộp màn hình AddMoreInfo và Update Profile là 1: Update Profile |  | Medium | ThuyNDT | 2022-03-13 | 2022-03-07 | Closed | Updated
44 | A- Student/Guest find Mentor: 1. Search: - Name - Trường học - Email - SĐT 2. Filter: - Tỉnh: <all in db> - Chuyên môn: <all in db> - Giới tính: Nam/Nữ - Hình thức giảng dạy: Online/Offline - Học phí trung bình: <20.000đ/buổi; 20.000~50.000đ/buổi; 50.000~100.000đ/buổi; >100.000đ/buổi 3. Order by: - rating => created date |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
45 | B- Admin/Mod find Mentor: 1. Search: - Name - Trường học - Email - SĐT 2. Filter: - Tỉnh: <all in db> - Chuyên môn: <all in db> - Giới tính: Nam/Nữ - Rating: <1*, 1-2*, 2-3*, 3-4*, 4-5* 3. Order by: - created date |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
46 | C- Admin/Mod find Student: 1. Search: - Name - Trường học - Email - SĐT 2. Filter: - Tỉnh: <all in db> - Giới tính: Nam/Nữ 3. Order by: - created date |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
47 | D- Admin find Mod: 1. Search: - Name - Email 2. Filter: <none> 3. Order by: - created date |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
48 | E- Mentor find Post: 1. Search: - Detail - Name (of creater) 2. Filter: - Chủ đề 3. Order by: - created date |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated
49 | F- Search Quiz (trên màn Thư viên của tôi) 1. Search: - Quiz name - Name (of creater) 2. Filter: - Số câu: 1-10, 10-20, 20-30, >30 - Chủ đề: <all in db> - Thời gian làm bài: <10p, 10p-30p, 30p-1h, >1h 3. Order by: - created date |  | Medium | ThuyNH | 2022-03-02 | 2022-03-07 | Closed | Updated

## Q&A
PROJECT Q&A
No | Date | Question | Creator | Priority | Status | PIC | Answer
1 | 2022-02-03 | Ngôn ngữ sử dụng default là tiếng việt hay tiếng anh? | ThuyNH | Low | Closed | LanLN | Tiếng Việt
2 | 2022-02-03 | Mật khẩu cần thỏa mãn điều kiện gì? Nhập quá bao nhiêu lần thì bị khóa tài khoản? | ThuyNH | Medium | Closed | ThuyNDT | Ít nhất 8 kí tự và có 1 chữ viết hoa. Nhập quá ???
3 | 2022-02-03 | Cả email và SĐT đều phải là unique có đúng ko? | ThuyNH | Medium | Closed | AnhDT | đúng
4 | 2022-02-03 | Ngay khi mới đăng ký thì trường users.enabled = 1 | ThuyNH | Medium | Closed | AnhDT | đúng
5 | 2022-02-03 | Nếu đăng ký bằng tài khoản gmail/facebook thì mật khẩu lưu trong database là gì? | ThuyNH | Medium | Closed | LanLN | Bỏ đăng ký bằng gmail/facebook
6 | 2022-02-03 | Nếu đăng ký bằng tài khoản gmail/facebook thì role là gì? | ThuyNH | Medium | Closed | LanLN | Bỏ đăng ký bằng gmail/facebook
7 | 2022-02-03 | đăng ký bằng facebook thì cũng lấy luôn email hoặc phone tương ứng vs thằng facebook đó đúng ko? | ThuyNH | Medium | Closed | LanLN | Bỏ đăng ký bằng facebook

## Defects
PROJECT DEFECTS
Issue Type | Issue key | Issue id | Summary | Assignee | Reporter | Priority | Status | Resolution | Created | Updated
Bug | CAPSTONE-459 | 10458 | [Bug] [BE] Can not login with new moderator account that create by admin | Tsunami | Tsunami | Highest | Done | Done | 2022-04-26 00:24 | 2022-04-26 09:29
Bug | CAPSTONE-458 | 10457 | [Bug] [BE] Bug avatar empty while chatting | Tuấn Anh TASS | Tsunami | High | Done | Done | 2022-04-26 00:17 | 2022-04-26 09:30
Bug | CAPSTONE-457 | 10456 | [Bug] [BE] Incorrect event when book request | Tuấn Anh TASS | Tsunami | Highest | Done | Done | 2022-04-24 10:54 | 2022-04-26 09:30
Bug | CAPSTONE-456 | 10455 | [Bug] [Mobile] UI of conversation list | Tsunami | Tsunami | Low | Done | Done | 2022-04-23 22:21 | 2022-04-25 22:18
Bug | CAPSTONE-454 | 10453 | [Bug] [Mobile] Bug search with empty token and filter | Tsunami | Tsunami | High | Done | Done | 2022-04-23 21:36 | 2022-04-25 22:18
Bug | CAPSTONE-453 | 10452 | [Bug] [Mobile] Text <giảng viên> is incorrect | Tsunami | Tsunami | Medium | Done | Done | 2022-04-23 21:28 | 2022-04-26 09:31
Bug | CAPSTONE-452 | 10451 | [Bug] [Mobile] Not udpate <Hình thức dạy học> when udpate profile | Tsunami | Tsunami | High | Done | Done | 2022-04-23 20:59 | 2022-04-25 22:22
Bug | CAPSTONE-451 | 10450 | [Bug] [Mobile] Crash when input enter in Introduce of Update Profile | Tsunami | Tsunami | Highest | Done | Done | 2022-04-23 20:56 | 2022-04-25 22:23
Bug | CAPSTONE-450 | 10449 | [Bug] [BE] Incorrect UI status of request when mentor view request detail | Tuấn Anh TASS | Tsunami | Highest | Done | Done | 2022-04-23 20:27 | 2022-04-26 09:30
Bug | CAPSTONE-449 | 10448 | [Bug] [Mobile] UI of Event Detail is not suitable | Tsunami | Tsunami | High | Done | Done | 2022-04-23 20:16 | 2022-04-25 22:24
Bug | CAPSTONE-448 | 10447 | [Bug] [BE] Still cache detail request when change status of request | Tuấn Anh TASS | Tsunami | Highest | Done | Done | 2022-04-23 19:55 | 2022-04-26 09:30
Bug | CAPSTONE-447 | 10446 | [Bug] [BE] Invalid warning when mentor agree/reject request right at the time student cancel | Tuấn Anh TASS | Tsunami | High | Done | Done | 2022-04-23 19:50 | 2022-04-26 09:30
Bug | CAPSTONE-446 | 10445 | [Bug] [Mobile] Crash when input enter in Create New Request Mentor | Tsunami | Tsunami | Highest | Done | Done | 2022-04-23 19:48 | 2022-04-24 10:50
Bug | CAPSTONE-441 | 10440 | [Bug] [Mobile] Bug invalid warning when error notification | Tsunami | Tsunami | High | Cancel |  | 2022-04-21 11:25 | 2022-04-23 22:07
Bug | CAPSTONE-439 | 10438 | [Bug] [BE UI of notification present not UTF-8 | Tsunami | Tsunami | High | Done | Done | 2022-04-21 11:04 | 2022-04-26 09:31
Bug | CAPSTONE-437 | 10436 | [Bug] [Mobile] Bug UI chatting | Tsunami | Tsunami | Medium | Done | Done | 2022-04-21 00:37 | 2022-04-24 09:24
Bug | CAPSTONE-436 | 10435 | [Bug] [Mobile] Bug wrong mess when enter invalid OTP | Tsunami | Tsunami | High | Done | Done | 2022-04-21 00:18 | 2022-04-25 22:25
Bug | CAPSTONE-435 | 10434 | [Bug] [Mobile] Crash when input enter in Creaa New Post Screen | Tsunami | Tsunami | Highest | Done | Done | 2022-04-20 23:55 | 2022-04-24 10:50
Bug | CAPSTONE-431 | 10430 | [Bug] [Mobile] Bug when lock account | Tsunami | Tsunami | High | Done | Done | 2022-04-18 22:58 | 2022-04-23 21:47
Bug | CAPSTONE-430 | 10429 | [Bug] [Mobile] Bug when disconnect to internet/server | Thuy Nguyen | Tsunami | High | Cancel |  | 2022-04-18 22:57 | 2022-04-22 04:12
Bug | CAPSTONE-429 | 10428 | [Bug] [Mobile] Keyboard of input comment | Tsunami | Tsunami | Low | Cancel |  | 2022-04-18 01:34 | 2022-04-18 22:57
Bug | CAPSTONE-428 | 10427 | [Bug] [Mobile] Confirm dialog when user decide to take quiz | Tsunami | Tsunami | Low | Done | Done | 2022-04-18 01:34 | 2022-04-19 21:24
Bug | CAPSTONE-427 | 10426 | [Bug] [Mobile] Sort criteria of events | Tsunami | Tsunami | Medium | Done | Done | 2022-04-18 01:31 | 2022-04-23 21:51
Bug | CAPSTONE-426 | 10425 | [Bug] [Mobile] Bị nháy màn hình khi thay đổi hình thức dạy | Tsunami | Tsunami | Medium | Cancel |  | 2022-04-18 01:29 | 2022-04-18 22:50
Bug | CAPSTONE-425 | 10424 | [Bug] [Mobile] Miss item phone on profile | Tsunami | Tsunami | Medium | Done | Done | 2022-04-17 22:14 | 2022-04-19 21:24
Bug | CAPSTONE-424 | 10423 | [Bug] [BE] Bug question list is not follow by created order | Tsunami | Tsunami | Medium | Done | Done | 2022-04-17 22:07 | 2022-04-23 21:46
Bug | CAPSTONE-423 | 10422 | [Bug] [Mobile] Bug warning when mentor view mentor's feedback screen | Tsunami | Tsunami | High | Done | Done | 2022-04-17 21:09 | 2022-04-21 00:31
Bug | CAPSTONE-420 | 10419 | [Bug] [Mobile] Can not remove reaction | Tsunami | Tsunami | Highest | Done | Done | 2022-04-17 01:18 | 2022-04-21 10:56
Bug | CAPSTONE-419 | 10418 | [Mobile] [UI] Responsive comment post | Thuy Nguyen | Dinh Tuan Anh (K14 HL) | Medium | Done | Done | 2022-04-16 06:35 | 2022-04-26 09:29
Bug | CAPSTONE-418 | 10417 | [Bug] [BE] Status of user can not update real time when active.inactive account | Tsunami | Tsunami | Highest | Done | Done | 2022-04-15 23:24 | 2022-04-21 10:56
Bug | CAPSTONE-417 | 10416 | [Bug] [Mobile] UI of icon react on the post | Tsunami | Ngọc Lan | Medium | Done | Done | 2022-04-15 00:03 | 2022-04-19 21:25
Bug | CAPSTONE-416 | 10415 | [Bug] [Mobile] Can not react to the post | Tsunami | Ngọc Lan | High | Done | Done | 2022-04-15 00:02 | 2022-04-19 21:25
Bug | CAPSTONE-415 | 10414 | [Bug] [Mobile] Avatar not round | Tsunami | Ngọc Lan | Medium | Done | Done | 2022-04-14 23:42 | 2022-04-19 21:25
Bug | CAPSTONE-414 | 10413 | [Bug] [Mobile] Bug udpate Hình thức học on mentor profile | Tsunami | Tsunami | High | Done | Done | 2022-04-13 20:46 | 2022-04-19 21:25
Bug | CAPSTONE-412 | 10411 | [Bug] [Mobile] [Backend] Add msg code when removing quiz/mentor from the favorite list | Tsunami | Ngọc Lan | Medium | Done | Done | 2022-04-13 13:11 | 2022-04-19 21:25
Bug | CAPSTONE-411 | 10410 | [Bug] [Backend] Error when register account with an email, but postman still create user successfully | Tsunami | Ngọc Lan | Medium | Done | Done | 2022-04-13 08:00 | 2022-04-23 21:48
Bug | CAPSTONE-410 | 10409 | [Bug] [Backend] Msg code is not clear when enter email which is not registered before in forgot password screen | Tsunami | Ngọc Lan | Medium | Done | Done | 2022-04-13 07:58 | 2022-04-21 00:32
Bug | CAPSTONE-409 | 10408 | [Bug] [Mobile] [Backend] Msg code when type email not well format in login screen | Tsunami | Ngọc Lan | Medium | Done | Done | 2022-04-12 20:24 | 2022-04-21 00:32
Bug | CAPSTONE-408 | 10407 | [Bug] [Mobile] Remove "Phone" in login label | Tsunami | Ngọc Lan | Low | Done | Done | 2022-04-12 20:21 | 2022-04-19 21:25
Bug | CAPSTONE-407 | 10406 | [Bug] [Mobile] Can not click option <Yêu cầu tìm gia sư mới nhất> | Tsunami | Tsunami | High | Done | Done | 2022-04-12 02:21 | 2022-04-19 21:25
Bug | CAPSTONE-406 | 10405 | [Bug] [Mobile] Can not click option <Những giảng viên tốt nhất> | Tsunami | Tsunami | High | Done | Done | 2022-04-12 02:20 | 2022-04-19 21:25
Bug | CAPSTONE-405 | 10404 | [Bug] [Mobile] Rating of mentor is not round up to 1 decimal digit | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 02:16 | 2022-04-19 21:25
Bug | CAPSTONE-404 | 10403 | [Bug] [Mobile] Bug layout when panning the screen | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 02:11 | 2022-04-19 21:25
Bug | CAPSTONE-403 | 10402 | [Bug] [Mobile] Bug missing mark of current date on schedule | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 01:55 | 2022-04-24 09:24
Bug | CAPSTONE-402 | 10401 | [Bug] [Mobile] Bug UI of textbox Comment on Feedback | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 01:52 | 2022-04-19 21:25
Bug | CAPSTONE-401 | 10400 | [Bug] [Mobile] Bug UI of textbox Search | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 01:52 | 2022-04-19 21:25
Bug | CAPSTONE-400 | 10399 | [Bug] [Mobile] Bug UI of textbox Repeat on Mentorship Request screen | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 01:51 | 2022-04-19 21:25
Bug | CAPSTONE-399 | 10398 | [Bug] [Mobile] Bug UI of textbox Detail on Mentorship Request screen | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 01:49 | 2022-04-19 21:25
Bug | CAPSTONE-398 | 10397 | [Bug] [Mobile] Bug UI of textbox Study Fee on Mentorship Request screen | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 01:49 | 2022-04-19 21:25
Bug | CAPSTONE-397 | 10396 | [Bug] [Mobile] Bug UI of textbox Study Fee on Mentor-finding Post screen | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 01:48 | 2022-04-19 21:25
Bug | CAPSTONE-396 | 10395 | [Bug] [Mobile] Bug UI of textbox Detail on Mentor-finding Post screen | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 01:47 | 2022-04-19 21:25
Bug | CAPSTONE-395 | 10394 | [Bug] [Mobile] Bug check maximum of total question on Create Quiz screen | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 01:43 | 2022-04-19 21:25
Bug | CAPSTONE-394 | 10393 | [Bug] [Mobile] Bug UI of textbox Answer on Create Quiz screen | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 01:41 | 2022-04-19 21:25
Bug | CAPSTONE-393 | 10392 | [Bug] [Mobile] Bug UI of textbox Question on Create Quiz screen | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 01:40 | 2022-04-19 21:25
Bug | CAPSTONE-392 | 10391 | [Bug] [Mobile] Bug UI of textbox Quiz Name on Create Quiz screen | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 01:39 | 2022-04-19 21:25
Bug | CAPSTONE-391 | 10390 | [Bug] [Mobile] Bug UI of textbox Password on Login screen | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 01:38 | 2022-04-19 21:25
Bug | CAPSTONE-390 | 10389 | [Bug] [Mobile] Bug UI of textbox Email on Login screen | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 01:37 | 2022-04-19 21:25
Bug | CAPSTONE-389 | 10388 | [Bug] [Mobile] Bug UI of textbox Studey Fee on Update Profile screen | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 01:37 | 2022-04-19 21:25
Bug | CAPSTONE-388 | 10387 | [Bug] [Mobile] Bug UI of textbox Phone on Update Profile screen | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 01:36 | 2022-04-19 21:25
Bug | CAPSTONE-387 | 10386 | [Bug] [Mobile] Bug UI of textbox Introduce on Update Profile screen | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 01:35 | 2022-04-19 21:25
Bug | CAPSTONE-386 | 10385 | [Bug] [Mobile] Bug UI of textbox Office on Update Profile screen | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 01:35 | 2022-04-19 21:25
Bug | CAPSTONE-385 | 10384 | [Bug] [Mobile] Bug UI of textbox Name on Update Profile screen | Tsunami | Tsunami | Medium | Done | Done | 2022-04-12 01:32 | 2022-04-19 21:25
Bug | CAPSTONE-384 | 10383 | [Bug] [Mobile] Bug publish quiz | Tsunami | Tsunami | High | Done | Done | 2022-04-12 00:52 | 2022-04-19 21:25
Bug | CAPSTONE-383 | 10382 | [Bug] [Mobile] Bug create quiz | Tsunami | Tsunami | Highest | Done | Done | 2022-04-12 00:50 | 2022-04-19 21:25
Bug | CAPSTONE-382 | 10381 | [Bug] [Mobile] Bug UI of taken quiz history | Tsunami | Ngọc Lan | High | Done | Done | 2022-04-12 00:30 | 2022-04-19 21:25
Bug | CAPSTONE-381 | 10380 | [Bug] [Mobile] Bug not limit access do quiz of deactive account | Tsunami | Ngọc Lan | High | Done | Done | 2022-04-12 00:29 | 2022-04-23 21:49
Bug | CAPSTONE-380 | 10379 | [Bug] [Mobile] Bug not limit access update profile of deactive account | Tsunami | Ngọc Lan | High | Done | Done | 2022-04-12 00:26 | 2022-04-24 23:13
Bug | CAPSTONE-379 | 10378 | [Bug] [Mobile] Bug not limit access change avatar of deactive account | Tsunami | Ngọc Lan | High | Done | Done | 2022-04-12 00:23 | 2022-04-25 22:47
Bug | CAPSTONE-378 | 10377 | [Bug] [Mobile] Profile of rejected mentor | Tsunami | Ngọc Lan | High | Done | Done | 2022-04-12 00:19 | 2022-04-19 21:25
Bug | CAPSTONE-377 | 10376 | [Bug] [Mobile] Layout of rejected mentor | Tsunami | Ngọc Lan | Highest | Done | Done | 2022-04-12 00:08 | 2022-04-19 21:25
Bug | CAPSTONE-376 | 10375 | [Bug] [Mobile] User cannot take any quiz | Tsunami | Ngọc Lan | Highest | Done | Done | 2022-04-11 20:00 | 2022-04-19 21:24
Bug | CAPSTONE-375 | 10374 | [Bug] [Mobile] Guest can access to edit quiz screen | Tsunami | Ngọc Lan | Medium | Done | Done | 2022-04-11 19:45 | 2022-04-19 21:24
Bug | CAPSTONE-374 | 10373 | [Bug] [Mobile] Heart icon in guest quiz overview screen | Tsunami | Ngọc Lan | Medium | Done | Done | 2022-04-11 19:43 | 2022-04-19 21:24
Bug | CAPSTONE-373 | 10372 | [Bug] [Mobile] Guest feedback mentor | Tsunami | Tsunami | High | Done | Done | 2022-04-11 19:41 | 2022-04-19 21:24
Bug | CAPSTONE-372 | 10371 | [Bug] [Mobile] Bug time of each <Ca học> | Thuy Nguyen | Tsunami | High | Cancel |  | 2022-04-11 19:35 | 2022-04-15 02:46
Bug | CAPSTONE-371 | 10370 | [Bug] [Mobile] Can not input item <Lặp lại> in new mentorship request | Tsunami | Tsunami | High | Done | Done | 2022-04-11 19:33 | 2022-04-19 21:24
Bug | CAPSTONE-370 | 10369 | [Bug] [Mobile] Crash app when input too much <Chi tiết> in New Mentorship Request | Tsunami | Tsunami | Highest | Cancel |  | 2022-04-11 19:31 | 2022-04-19 00:13
Bug | CAPSTONE-369 | 10368 | [Bug] [Mobile] Cannot delete existed feedback | Tsunami | Tsunami | Medium | Done | Done | 2022-04-11 19:14 | 2022-04-20 23:42
Bug | CAPSTONE-368 | 10367 | [Bug] [Mobile] Crash app when input too much <Nhận xét> in New Feedback | Tsunami | Tsunami | Highest | Cancel |  | 2022-04-11 19:10 | 2022-04-19 00:13
Bug | CAPSTONE-367 | 10366 | [Bug] [Mobile] Show exception when input to much text <Họ và tên> in update profile | Tsunami | Tsunami | Highest | Done | Done | 2022-04-11 19:07 | 2022-04-19 21:24
Bug | CAPSTONE-366 | 10365 | [Bug] [Mobile] Crash app when input to much text <Giới thiệu> in update profile | Tsunami | Tsunami | Highest | Cancel |  | 2022-04-11 19:05 | 2022-04-19 00:13
Bug | CAPSTONE-365 | 10364 | [Bug] [Mobile] Update profile with invalid phone | Tsunami | Tsunami | High | Done | Done | 2022-04-11 18:57 | 2022-04-19 21:24
Bug | CAPSTONE-364 | 10363 | [Bug] [Mobile] Enter a email that not exist when forgot password | Tsunami | Tsunami | Medium | Done | Done | 2022-04-11 15:53 | 2022-04-19 21:24
Bug | CAPSTONE-363 | 10362 | [Bug] [Mobile] Test UI of <Forgot Password> screen | Tsunami | Tsunami | Medium | Done | Done | 2022-04-11 15:49 | 2022-04-19 21:24
Bug | CAPSTONE-362 | 10361 | [Bug] [Mobile] Test notification of each role | Tsunami | Tsunami | Medium | Done | Done | 2022-04-11 15:31 | 2022-04-19 21:24
Bug | CAPSTONE-361 | 10360 | [Bug] [Mobile] UI of Setting screen | Tsunami | Tsunami | Medium | Done | Done | 2022-04-11 15:27 | 2022-04-20 23:45
Bug | CAPSTONE-359 | 10358 | [Bug] [Mobile] UI of filter Học phí trung bình | Tsunami | Tsunami | Medium | Done | Done | 2022-04-10 14:56 | 2022-04-19 21:24
Bug | CAPSTONE-358 | 10357 | [Bug] [Mobile] UI for icon Notification | Tsunami | Tsunami | Medium | Done | Done | 2022-04-10 14:43 | 2022-04-21 01:19
Bug | CAPSTONE-355 | 10354 | [Bug] [Mobile] Crash app when take quiz | Tsunami | Tsunami | Highest | Done | Done | 2022-04-09 01:37 | 2022-04-19 21:25
Bug | CAPSTONE-353 | 10352 | [Bug] [Mobile] Search mentor-finding post with token empty | Tsunami | Tsunami | High | Cancel |  | 2022-04-09 01:28 | 2022-04-09 15:31
Bug | CAPSTONE-352 | 10351 | [Bug] [Mobile] Admin search account with token empty | Tsunami | Tsunami | High | Cancel |  | 2022-04-09 01:26 | 2022-04-09 15:31
Bug | CAPSTONE-351 | 10350 | [Bug] [Mobile] Search quiz with token empty | Tsunami | Tsunami | High | Cancel |  | 2022-04-09 01:25 | 2022-04-09 15:33
Bug | CAPSTONE-350 | 10349 | [Bug] [Mobile] Student search mentor with token empty | Tsunami | Tsunami | High | Cancel |  | 2022-04-09 01:22 | 2022-04-09 15:33
Bug | CAPSTONE-349 | 10348 | [Bug] [Mobile] Crash app when input too much <Chi tiết> in New Mentorship Request | Tsunami | Tsunami | Highest | Cancel |  | 2022-04-09 00:58 | 2022-04-19 00:13
Bug | CAPSTONE-348 | 10347 | [Bug] [Mobile] Crash app when input too much <Học phí> in New Mentor-finding Post | Tsunami | Tsunami | Highest | Done | Done | 2022-04-08 23:55 | 2022-04-19 21:24
Bug | CAPSTONE-347 | 10346 | [Bug] [Mobile] Warning when disconnect to wifi/server | Thuy Nguyen | Tsunami | High | Cancel |  | 2022-04-08 22:14 | 2022-04-22 04:14
Bug | CAPSTONE-346 | 10345 | [Bug] [Mobile] Crash app when take quiz 0 question | Tsunami | Tsunami | Highest | Done | Done | 2022-04-08 22:11 | 2022-04-19 21:25
Bug | CAPSTONE-345 | 10344 | [Bug] [Mobile] Wrong screen for role rejected pending mentor | Tsunami | Ngọc Lan | High | Cancel |  | 2022-04-07 23:20 | 2022-04-19 00:06
Bug | CAPSTONE-344 | 10343 | [Bug] [Mobile] After changing password, the app not auto back to settings | Tsunami | Ngọc Lan | Medium | Done | Done | 2022-04-07 23:19 | 2022-04-19 21:24
Bug | CAPSTONE-343 | 10342 | [Bug] [Mobile] Default avatar is not match between profile screen and home screen | Tsunami | Ngọc Lan | Low | Done | Done | 2022-04-07 22:54 | 2022-04-20 23:52
Bug | CAPSTONE-342 | 10341 | [Bug] [Backend] Some choices below province/city level is empty | Tsunami | Ngọc Lan | Medium | Done | Done | 2022-04-07 15:31 | 2022-04-19 21:24
Bug | CAPSTONE-341 | 10340 | [Bug] [Mobile] [Backend] Error when entering email login with space before/after email text | Tsunami | Ngọc Lan | Highest | Done | Done | 2022-04-07 15:30 | 2022-04-19 21:25
Bug | CAPSTONE-340 | 10339 | [Bug][Mobile] bug do not update enabled status UI | Tsunami | Dinh Tuan Anh (K14 HL) | Medium | Done | Done | 2022-04-07 14:59 | 2022-04-23 21:46
Bug | CAPSTONE-339 | 10338 | [Bug] [Mobile] Test UI of Quiz Overview | Tsunami | Tsunami | High | Done | Done | 2022-04-06 20:35 | 2022-04-19 21:24
Bug | CAPSTONE-338 | 10337 | [Bug] [Mobile] Test adding a favorite mentor | Tsunami | Tsunami | Low | Cancel |  | 2022-04-06 02:47 | 2022-04-09 00:09
Bug | CAPSTONE-337 | 10336 | [Bug] [Mobile] Test UI for <Filter Criteria of Mentor List> screen by admin/moderator view | Tsunami | Tsunami | Medium | Cancel |  | 2022-04-06 02:44 | 2022-04-09 00:11
Bug | CAPSTONE-336 | 10335 | [Bug] [Mobile] Test to filter list mentor via desired fields navigated from student/guest view | Tsunami | Tsunami | High | Done | Done | 2022-04-06 02:41 | 2022-04-24 10:52
Bug | CAPSTONE-332 | 10331 | [Bug] [Mobile] Test UI of <Detail Mentorship Request> viewed by mentor role | Tsunami | Tsunami | Medium | Done | Done | 2022-04-01 15:51 | 2022-04-19 21:24
Bug | CAPSTONE-331 | 10330 | [Bug] [Mobile] Test UI of all mentorship list screen | Tsunami | Tsunami | Low | Cancel |  | 2022-04-01 15:48 | 2022-04-09 01:08
Bug | CAPSTONE-330 | 10329 | [Bug] [Mobile] Test warning when input missing required information | Tsunami | Tsunami | Medium | Done | Done | 2022-04-01 15:43 | 2022-04-19 21:24
Bug | CAPSTONE-328 | 10327 | [Bug] [Mobile] Test update overview quiz | Tsunami | Tsunami | Highest | Done | Done | 2022-04-01 15:26 | 2022-04-19 21:24
Bug | CAPSTONE-327 | 10326 | [Bug] [Mobile] Test UI for <Registered Mentor Profile> screen when admin/moderator choose from Registered Mentor List | Tsunami | Tsunami | High | Done | Done | 2022-04-01 15:19 | 2022-04-19 21:24
Bug | CAPSTONE-325 | 10324 | [Bug] [Mobile] Test display when the list of registered mentor is empty | Tsunami | Tsunami | Low | Done | Done | 2022-04-01 15:16 | 2022-04-19 21:24
Bug | CAPSTONE-324 | 10323 | [Bug] [Mobile] Test display when the list of mentor is empty | Tsunami | Tsunami | Low | Done | Done | 2022-04-01 15:12 | 2022-04-19 21:24
Bug | CAPSTONE-321 | 10320 | [Bug] [Mobile] App crash when starting a quiz, next ques | Tsunami | Ngọc Lan | Highest | Done | Done | 2022-03-21 23:51 | 2022-04-19 21:24
Bug | CAPSTONE-320 | 10319 | [Bug] [Mobile] Hide 'Liên hệ học sinh' when admin/mod views student post | Tsunami | Tsunami | High | Done | Done | 2022-03-21 17:29 | 2022-04-19 21:24
Bug | CAPSTONE-319 | 10318 | [Bug] [Mobile] Test UI for <Student Profile> screen | Tsunami | Tsunami | High | Cancel |  | 2022-03-21 15:40 | 2022-04-12 00:46
Bug | CAPSTONE-318 | 10317 | [Bug] [Mobile] Fix textview padding | Tsunami | Ngọc Lan | High | Done | Done | 2022-03-21 12:48 | 2022-04-19 21:24
Bug | CAPSTONE-317 | 10316 | [Bug] [Mobile] Test UI for <Detail Quiz Result> screen. | Tsunami | Tsunami | High | Done | Done | 2022-03-20 23:36 | 2022-04-21
Bug | CAPSTONE-316 | 10315 | [Bug] [Mobile] Test flow back when unfinished quiz | Tsunami | Tsunami | Medium | Done | Done | 2022-03-20 23:33 | 2022-04-19 21:25
Bug | CAPSTONE-315 | 10314 | [Bug] [Mobile] Test create quiz | Tsunami | Tsunami | Highest | Done | Done | 2022-03-20 23:25 | 2022-04-19 21:25
Bug | CAPSTONE-314 | 10313 | [Bug] [Mobile] Test UI for <My Quiz Overview> screen that navigated from own profile. | Tsunami | Tsunami | High | Done | Done | 2022-03-20 23:23 | 2022-04-19 21:25
Bug | CAPSTONE-313 | 10312 | [Bug] [Mobile] Test UI for <My Draft Quiz Overview> | Tsunami | Tsunami | High | Done | Done | 2022-03-20 23:20 | 2022-04-19 21:25
Bug | CAPSTONE-312 | 10311 | [Bug] [Mobile] Test UI for <My Quiz Overview> | Tsunami | Tsunami | High | Done | Done | 2022-03-20 23:19 | 2022-04-19 21:25
Bug | CAPSTONE-311 | 10310 | [Bug] [Mobile] Test UI for <My Quiz List> screen | Tsunami | Tsunami | High | Done | Done | 2022-03-20 23:16 | 2022-04-19 21:24
Bug | CAPSTONE-310 | 10309 | [Bug] [Mobile] Test display for empty list | Tsunami | Tsunami | Low | Done | Done | 2022-03-20 23:03 | 2022-04-19 21:24
Bug | CAPSTONE-309 | 10308 | [Bug] [Mobile] Test update profile | Tsunami | Tsunami | High | Done | Done | 2022-03-20 22:57 | 2022-04-19 21:24
Bug | CAPSTONE-308 | 10307 | [Bug] [Mobile] Test UI for student/mentor profile screen. | Tsunami | Tsunami | Low | Done | Done | 2022-03-20 22:53 | 2022-04-21 01:19
Bug | CAPSTONE-307 | 10306 | [Bug] [Mobile] Test the warning when the confirm password does not match | Tsunami | Tsunami | Low | Done | Done | 2022-03-20 22:50 | 2022-04-19 21:24
Bug | CAPSTONE-306 | 10305 | [Bug] [Mobile] Test the warning when input invalid password. | Tsunami | Tsunami | High | Done | Done | 2022-03-20 22:48 | 2022-04-19 21:24
Bug | CAPSTONE-305 | 10304 | [Bug] [Mobile] Test resent OTP | Tsunami | Tsunami | High | Cancel |  | 2022-03-20 22:45 | 2022-04-21 00:15
Bug | CAPSTONE-304 | 10303 | [Bug] [Mobile] Test lock account when input incorrent OTP 6 times in a row. | Tsunami | Tsunami | Medium | Cancel |  | 2022-03-20 22:42 | 2022-04-12 00:54
Bug | CAPSTONE-303 | 10302 | [Bug] [Mobile] Test the warning when input incorrect OTP | Tsunami | Tsunami | Low | Done | Done | 2022-03-20 22:41 | 2022-04-19 21:24
Bug | CAPSTONE-302 | 10301 | [Bug] [Mobile] Test UI for <Verify OTP> screen | Tsunami | Tsunami | High | Done | Done | 2022-03-20 22:38 | 2022-04-19 21:25
Bug | CAPSTONE-301 | 10300 | [Bug] [Mobile] Test the warning when input inactive account. | Tsunami | Tsunami | High | Done | Done | 2022-03-20 22:36 | 2022-04-19 21:25
Bug | CAPSTONE-300 | 10299 | [Bug] [Mobile] Test the warning when input invalid email. | Tsunami | Tsunami | Medium | Done | Done | 2022-03-20 22:33 | 2022-04-19 21:25
Bug | CAPSTONE-299 | 10298 | [Bug] [Mobile] Test UI of deactive submit button when input missing required additional information. | Tsunami | Tsunami | High | Done | Done | 2022-03-20 22:29 | 2022-04-19 21:25
Bug | CAPSTONE-298 | 10297 | [Bug] [Mobile] Test UI for <Add More Information> screen | Tsunami | Ngọc Lan | High | Done | Done | 2022-03-20 22:16 | 2022-04-19 21:24
Bug | CAPSTONE-297 | 10296 | [Bug] [Mobile] Crash App when clicking my detail mentorship request | Tsunami | Ngọc Lan | Highest | Done | Done | 2022-03-19 12:05 | 2022-04-19 21:24
Bug | CAPSTONE-294 | 10293 | [Bug] [Mobile] Mentorship Request List in Profile is not updated | Tsunami | Tuấn Anh TASS | High | Done | Done | 2022-03-17 20:17 | 2022-04-19 21:24
Bug | CAPSTONE-293 | 10292 | [Bug] [Mobile] Enter long text in create post description | Tsunami | Tuấn Anh TASS | High | Done | Done | 2022-03-17 19:34 | 2022-04-19 21:24
Bug | CAPSTONE-292 | 10291 | [Bug] [Mobile] Test the warning when the confirm password does not match | Tsunami | Ngọc Lan | Low | Done | Done | 2022-03-17 19:30 | 2022-04-19 21:24
Bug | CAPSTONE-291 | 10290 | [Bug] [Mobile] Test the warning when input invalid new password | Tsunami | Ngọc Lan | High | Done | Done | 2022-03-17 19:28 | 2022-04-19 21:24
Bug | CAPSTONE-290 | 10289 | [Bug] [Mobile] Test the warning when input incorect old password | Tsunami | Ngọc Lan | Low | Cancel |  | 2022-03-17 19:26 | 2022-04-09 01:16
Bug | CAPSTONE-289 | 10288 | [Bug] [Mobile] Test login to a deactive account | Tsunami | Ngọc Lan | Low | Done | Done | 2022-03-17 19:23 | 2022-04-19 21:24
Bug | CAPSTONE-288 | 10287 | [Bug] [Mobile] Test skip login | Tsunami | Ngọc Lan | High | Done | Done | 2022-03-17 19:21 | 2022-04-09 01:13
Bug | CAPSTONE-284 | 10283 | [BUG] [Mobile] quizzes history are not sorted by date | Tsunami | Thao Duong | High | Done | Done | 2022-03-17 00:32 | 2022-04-09 00:49
Bug | CAPSTONE-283 | 10282 | [Bug] [Mobile] Test to create an account | Tsunami | Ngọc Lan | Highest | Done | Done | 2022-03-16 22:59 | 2022-04-09 01:13
Bug | CAPSTONE-281 | 10280 | [Bug] [Mobile] Test the warning when not agree with term and policies | Tsunami | Ngọc Lan | Medium | Cancel |  | 2022-03-16 21:04 | 2022-04-21 00:15
Bug | CAPSTONE-280 | 10279 | [Bug] [Mobile] Test the warning when input invalid email | Tsunami | Ngọc Lan | High | Done | Done | 2022-03-16 21:03 | 2022-04-09 01:13
Bug | CAPSTONE-279 | 10278 | [Bug] [Mobile] Test the warning when input invalid phone | Tsunami | Ngọc Lan | Medium | Cancel |  | 2022-03-16 21:02 | 2022-04-12 00:56
Bug | CAPSTONE-278 | 10277 | [Bug] [Mobile] Test the warning when input invalid name | Tsunami | Ngọc Lan | High | Done | Done | 2022-03-16 20:58 | 2022-04-21 00:17
Bug | CAPSTONE-277 | 10276 | [Bug] [Mobile] Test the warning when the confirm password does not match | Tsunami | Ngọc Lan | High | Done | Done | 2022-03-16 20:57 | 2022-04-19 21:24
Bug | CAPSTONE-276 | 10275 | [Bug] [Mobile] Test the warning when input invalid password | Tsunami | Ngọc Lan | High | Done | Done | 2022-03-16 20:55 | 2022-04-19 21:24
Bug | CAPSTONE-275 | 10274 | [Bug] [Mobile] Test the warning when input duplicated phone | Thuy Nguyen | Ngọc Lan | High | Cancel |  | 2022-03-16 20:54 | 2022-04-12 00:51
Bug | CAPSTONE-274 | 10273 | [Bug] [Mobile] Test the warning when input duplicated email | Tsunami | Ngọc Lan | High | Cancel |  | 2022-03-16 20:52 | 2022-04-19 00:12
Bug | CAPSTONE-273 | 10272 | [Bug] [Mobile] Test UI for <Register Account> screen | Tsunami | Ngọc Lan | High | Done | Done | 2022-03-16 20:48 | 2022-04-21 00:17